## City liaison plan
Responsible party | Week before | Monday | Tuesday | Wed | Thurs | Fri | Sat /Sun | Monday | Later in week
Choura plan |  |  |  | Astroturf | Tents and staging | Rentals placed | Linens and Final | Take down
Other | Program phone numbers for all support folks in cell (speed dial) |  |  |  |  | Chalk Streets, Help with banner hanging | Check in on Trash (city and waste mgmt), Protime and Comms | Waste mgmt dir: All trash cleaned up off field | Write down lesson's learned
[6 empty] | Check ATM dropoff | Check in with KC, volunteers and free games | KC and BG director: Ensure all of our locks and chains were picked up | Bring hats for P&R and/or PW team members that didn’t receive them
|  | Comm Rel dirctor: Pick up Jenn Caskey banner is using | [5 empty] | Comm Rel dirctor: Bring Jenn Caskey banner back to P&R
Parks & Rec | Review closure signage | Reminder email about A frames drop off (if needed) |  |  |  | Check tennis courts and batting cages open
|  | Get names of rec workers from Michael Hudak | Check baseball banners down | Ensure basketball hoops and tot lot closed |  | Check A frame delivery - if borrowing | Podium in front of Joslyn | T&S directror: If using A frames, ensure all back to spot they were picked up.
PW | Review street and parking lot closure signage | Drop off 6 Banners w PW with photos of locations to hang | Resp for Waste mgmt dir: Check fencing/gate removal at dog park dn access to live oak and dorsey | Check banners up in appropriate spots | Check signage on street & parking lot closures |  |  |  | Pick up banners and bring back to storage
|  | Drop off final field maps w/ electircal; should have been coordinated prior week | Resp for Waste mgmt dir: Check service entrance on Dorsey and 20th | check wooden slats delivered | Check green belt access for KC | Check elecrical for BBQ plus all other elect OK and wire covers in place | Elect help as needed
|  |  |  | Check band shell in place | Check street cleanliness and basketball courts | check faucets at sinks and check for wood chips | ATM help as needed
|  |  | Support initial Field marking w Food/Games Directors | Support field marking | Check Joslyn locks changed | Check city trash | Check city trash
|  |  |  | Get keys | Check lights on fields and courts | Check lights on fields and courts | Check lights on fields and courts

## 2024 Lessons
Volunteers | Co chairs for Kid country, merch (or Dana's mom), info booth covered by Kim's folks,
KC | Separate big and little kids in bounices
Create height boards (ala Disneyland) to separate taller/smaller children
Consider differernt times for different sizes of kids
Consider differernt times for different sizes of kids
Consider no bouncies w/ long pathway where kids get stuck in middle
More senior/adult volunteer help at the bouncies?
1 more Park and Rec employee (from Free games?)
Buy 4 locks and chains for gates
Ensure 1 20 amp for EACH plug in inflatable blower - were we short 1?
Free games | Give up 1 Park and Rec employee to kid country?
Wine Garden | Any way to increase size Sat. afternoon?
Power in Wine garden by Thursday Morn
Bring chains to lock basketball courts?
Beer Garden | Buy lock/chain for emergency exit
Anyway to increase size Sat afternoon
Consider DJ (See Robin)
Ensure entry/exit signs - PW to get from yard
Main Stage | Speaker riser comes from Choura - it’s a box that speakers sit on to project into beer garden
Food/Games | Change application to read that Every electrical device will need 1 20 amp connection
- only issue was Pretzels due to 4 connections
No dogs in booths? (coffee folks had a pitbull)
Fix map to show Amps vs. watts. Need 20 Amps (1 plug) for every device
Better plan for bathrooms: Could we post notices and then not watch them?
Review field layout with PW early
Merch | Does contract allow for refunds if faulty merch?
Raffle/Donors | Get Jen Casky banners down on Monday; bring back next week to Michael Hudak
Community Showcase | all good?
Dietz | Keep same angle for stage? Seemed to work well.
Parking and Safety | Need to revise parking template for ATM guy - needs M, V, F, J
Will Joslyn parking lot support fair board members?
Buy our own A frames?
How to ensure cars in correct lanes?
Had a few cars that overshot their field and had to backup
Had cars that should have been on west side (100s) but were directed to east side (300s)
Consider only helping with bringing cars into entrance on Sunday eve.
Liability with helping vendors move items out of way?
Arts and Crafts | No dogs in booths?
See drivein/drive out thoughts in Parking and Safety
Waste mgmt | Need to clean up all fields after fair
City Liaison/ Public Works | Need a lead for each day, Friday thru Monday - from both Elect and maint.
Consider map that shows electrical location - the old cad drawing?
City Liaison/ City Letter | See letter for updates; need 2 plugs for ATM on Dorsey
Do not need P&R volunteer help on Thursday
Need more P&R voluntters in Kid Country help (only had 1) - borrow from free games?
Lock basketball courts on Wed
Ensure parking lot and street closure times are correct
Other | Need a closeout/cleanup process for Monday
Responsibility for Large banners, welcome/donor banners
How to get more done from Choura Wed/Thurs
Create a more detailed schedule - see below.
Meetings to have before fair: | Erik Lee | Need clear PW lead (Sean was MIA);
need lead for both elec and maint each day (including Monday)
| PW | Street closure clarity before signs made
Review electrical for booths early fair weekend
Specific plans/schedule for Week with PW - field marking, keys/locks,Aframes,
Need power in wine garden by Thurs.
| Tayleen | Permits
| Parks & Rec | Get support plan week of fair
Review signs for field closures
| Police and PW | Review parking lot and street Closure signage ftimes to ensure correct
CITY HALL Parking lot – (TOW AWAY, NO PARKING FROM 5 P.M. FRIDAY TO 10:00 P.M. SUNDAY).
JOSLYN/Post Office Parking Lot – (TOW AWAY, NO PARKING FROM 8 A.M. FRIDAY TO 10:00 P.M. SUNDAY).
End of 16th Place and 18th Place (behind Joslyn Center) (TOW AWAY - DO NOT BLOCK)
Parking LOT 8 – (TOW AWAY - NO PARKING FROM 6:00 A.M. FRIDAY TO 10:00 P.M. SUNDAY).
Valley Drive, East side from Blanche to 15th – TOW AWAY, NO Parking 6:00 A.M. FRI. to10:00 P.M. SUN.
Valley Drive, West side from Blanche to 21st – TOW AWAY, NO PARKING 6:00 A.M. FRI. to 10:00 P.M. SUN.
Valley Drive, West side from Live Oak to 15th – TOW AWAY, NO PARKING 6:00 A.M. FRI. to 10:00 P.M. SUN.
Valley Drive, West side from 21st to Live Oak Park. TOW AWAY, NO PARKING 6:00 A.M. FRI TO 2:00 P.M. MON..
Area must be clear of cars for pick-up/roll off on Monday.
Create a more detailed schedule | Monday: Drop off large banners; REMOVE Jenn Casky banner if needed for beer garden
Tuesday:
7am: Large waste bins go on behind wine garden
9am? PW starts marking field booths – need to ensure grass has been mowed first
PW puts up 6 large venue banners - need to provide photos of locations
Wednesday 12PM+: Astroturf installation
More waste bins?
With PW complete field booth marking and banners
PW electrical
Get keys from PW
Thursday: Tents and Staging
Uhaul Pickup
Field numbering
PW rekeys Joslyn
Friday: Rentals placed (tables and chairs)
P&R supports street chalking
Saturday: Linens and touch-ups
Sunday: Clear Sunset room by 10pm
Monday: Uhaul back to storage
Clear Sunrise room by 3pm.

## Other things to consider
Secretary | Get rid of table tents - have everyone wear their badges at beginning of year; buy some stickons